## Slide 1: Plan and Schedule Directions Grading Rubric

## Slide 2: Plan and Schedule
Plan and Schedule MUST Include
  Schedule and Tasks for Completion of the Design
    Task Name
    Planned Start and End Date of Task
    Estimated Total Hours for Task
    Actual Start and End Date of Task (added after task completed)
    Actual Total Hours for Task (added after task completed)
    The Team Member Responsible for Completing Each Task
      “All” is not a Team Member!
      If Multiple Team Members Work on a Task Designate One Team Member Responsible for Its Completion.
  Notes: Your Plan and Schedule is not simply an administrative task. It should be a “checklist” of everything that needs to be done to successfully complete your project and show that it meets your customer’s requirements.

## Slide 3: Format for Plan and Schedule
 |  |  |  |  |  |  | SCHEDULE (WEEK ENDING) |  |  |  |  | 
TASK ID | TASK DESCRIPTION | RESPONSIBLE TEAM MEMBER | PLANNED TOTAL HOURS | Jan 26 | Feb 2 | - - - - | Mar 2 | - - - | Mar 30 | - - - | May 2- 3 | ACTUAL TOTAL HOURS
 | Plan and Schedule |  |  |  | Δ |  |  |  |  |  |  | 
 | Test Plan |  |  |  |  |  | Δ |  |  |  |  | 
 | Test Report |  |  |  |  |  |  |  | Δ |  |  | 
 | Final Report |  |  |  |  |  |  |  |  |  | Δ | 
 | Final Presentation and Demo |  |  |  |  |  |  |  |  |  | Δ | 
Plan
Actual
T2
T1
Task XYZ

## Slide 4: Guidelines for Plan and Schedule
The Application Used to Build the Schedule is Your Choice
  Microsoft Project
  Excel
  Other
The “Actual Hours” Column on the Right Will be Filled in as Tasks are Completed
The Actual Start and Finish Dates Will be Filled in When Tasks are Begun and then when Completed
Use Units of Weeks (15 total including break)- This will Keep the Schedule to a Manageable Size. If Desired, You Can Add a Lower Level of Detail Either by Adding Additional Columns on Left (If you do this, Microsoft Project is suggested) or Including the Dates at the Beginning and End of the Task Bars

## Slide 5: “Task Description ” Column in the Schedule
Define Tasks to Ensure That All Parts of the Project are Addressed
  Hardware
  Software
  Electrical
  Interfaces
  Test and Demonstrations
  Reviews
The Best Way to Ensure That All Tasks Are Specified is to Correlate the Tasks to the Following:
  System Description
    This will ensure that all parts of your project are addressed
  Tests Supporting the Verification of Requirements
    Requirements Form the Basis for Test- Related Tasks
  Assignments and Due Dates
    Listed at the Top of the Schedule for Reference

## Slide 6: Format for Plan and Schedule Report
Title Page
  System Overview
  Include CON-Ops, System Block Diagrams, Software Diagrams, Hardware and Electronics Drawings as Applicable
  Reuse Material from ECE 457 as Applicable
  Include any Updates Since ECE 457 PDR
Table Showing Current Engineering Requirements
  Reuse Earlier Tables Presented in ECE 457 PDR
  Include any Updates since PDR
Schedule
Use Format Shown
Include the following information for each task:
    Task Name
    Planned Start and End Date of Task
    Estimated Total Hours for Task
    Team Member Responsible for the Task

## Slide 7: Notes on Plan and Schedule Assignment
Title Page
  System Overview
  You should be able to reuse material produced in ECE 457 adding only updates for additional detail or changes based on customer/ advisor input.
Table Showing Current Engineering Requirements
  Same comment as above. You should be able to reuse your requirements tables from ECE 457 and add additional detail, new or changed requirements/sub-requirements. See next slide for requirements format.
Schedule
  If your schedule will not fit on one page (landscape mode suggested) then break it up over several pages. A logical, but not mandatory, place to break schedule is at the due dates for assignments.
  Notes: The System Overview and Requirements Tables are based on information previously developed. Reusing them minimizes your work and helps ensure consistency from one assignment to the next.
  Likewise, the Schedule will be reused and updated throughout the semester. Keep this in mind when developing it– anything you can do to make it easy to update will save work later.

## Slide 8: Grading Rubric for Plan and Schedule Assignment

## Slide 9: Directions for Submitting Plan and Schedule
Plan and Schedule Assignment is Due on Feb 4th by NOON
Place Plan and Schedule File on m: drive In Your Project Folder
Use the Following Naming Convention for the File
ECE-<N> Plan and Schedule.docx
N is the Number of Your Project
The Template for the Plan and Schedule is on the m: drive ECE458 Plan and Schedule Template.xlsx